## Meeting Content (hidden)
Capacity Senior Task Force Meeting Content
Meeting
| 1 | 2 | 3 | 4 | 5 | 6
| 9am-noon | 9am-noon | 9am-noon | 9am-noon | 9am-noon | 9am-noon
Topic(s) | 2012-04-12 | 2012-04-19 | 2012-04-27 | 2012-05-04 | 2012-05-22 | 2012-06-06 | 2012-06-28 | 2012-07-26 | 2012-08-01
Admin | bar: 2012-04-12
Charter | bar: 2012-04-12 to 2012-04-19
Work Plan | bar: 2012-04-12
Provide Education | bar: 2012-04-12
Document Interests | bar: 2012-04-19
Develop Design Components | bar: 2012-04-19 to 2012-04-27
Develop Solution Options | bar: 2012-04-27 to 2012-05-04
Reduce Solution Options | bar: 2012-05-04
Package Solutions | bar: 2012-05-04 to 2012-05-22
Reduce Package Options | bar: 2012-05-22 to 2012-06-06
Build Concensus | bar: 2012-06-06
Vote at MRC/MC | 2012-06-28: First Read; 2012-07-26: X
File with FERC | bar: 2012-08-01

## With dates (hidden)
2012- 2013 Capacity Senior Task Force Work Plan
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProvide Education
Proposal Development |  |  | 13 |  | 11
Decision Making | [5 empty] | 14 | 5
First Read @ MRC | [6 empty] | 20
Vote at MRC/MC
RTEP/Transmission Issues | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
Problem Investigation |  |  |  | 20
Proposal Development |  |  |  |  | 11
Decision Making | [5 empty] | 14 | 5
First Read @ MRC | [6 empty] | 20
Vote at MRC/MC
Demand Response Issues | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | Mar. 2013
üProvide Education
Document Interests |  |  |  | 20
Develop & Refine Design Components | [5 empty] | 14
Develop & Refine Solution Options | [6 empty] | 5
Develop & Refine Solution Packages
Build Consensus
First Read @ MRC
Vote at MRC/MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01
üProvide Education
Refine Interests |  |  | 13
Refine Design Components
Develop & Refine Solution Options |  |  |  |  | 2012-10-01: 11; 2012-11-01: 14
Develop & Refine Solution Packages |  |  |  |  | 2012-12-01: 5
Build Consensus | bar: 2013-01-01 to 2013-02-01
First Read @ MRC | bar: 2013-03-01
Vote at MRC/MC | bar: 2013-04-01
FERC Filing |  |  |  |  | 2013-05-01: 2012-05-31

## 2012- printable (hidden)
2012- 2013 Capacity Senior Task Force Work Plan
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
üProposal Development
Build Consensus
First Read @ MRC
Vote at MRC
Vote at MC
RTEP/Transmission Issues | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
Proposal Development
Build Consensus
First Read @ MRC
Vote at MRC
Vote at MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01
üProvide Education
üRefine Interests
üRefine Design Components
Develop & Refine Component Options | bar: 2012-10-01 to 2012-11-01
Develop & Refine Solution Packages | bar: 2012-11-01 to 2012-12-01
Build Consensus | bar: 2013-01-01 to 2013-02-01
First Read @ MRC | bar: 2013-03-01
Vote at MRC | bar: 2013-04-01
Vote at MC | bar: 2013-05-01
FERC Filing |  |  |  | 2013-05-01: 2012-05-31

## 2013- printable (hidden)
2012- 2013 Capacity Senior Task Force Work Plan
|  |  | 2012 |  |  |  | 2013
2012 Demand Response Issues | 2012-07-01 | 2012-08-01 | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
üProvide Education
Document Interests | bar: Oct
Develop & Refine Design Components | bar: Nov
Develop & Refine Component Options | bar: Dec to 2013 Jan
Develop & Refine Solution Packages | bar: 2013 Feb to 2013 Mar
Build Consensus | bar: 2013 Mar to 2013 Apr
First Read @ MRC | bar: 2013 Apr
Vote at MRC | bar: 2013 May
Vote at MC | bar: 2013 Jun
|  |  | 2012 | 2013 Jan: 2013
2013 Demand Response Issues | 2012-07-01 | 2012-08-01 | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Provide Education | bar: 2013 Jan
Document Interests | bar: 2013 Feb
Develop & Refine Design Components | bar: 2013 Feb to 2013 Mar
Develop & Refine Component Options | bar: 2013 Apr to 2013 May
Develop & Refine Solution Packages | bar: 2013 Jun
Build Consensus | bar: 2013 Jul to 2013 Aug
First Read @ MRC | bar: 2013 Sep
Vote at MRC | bar: 2013 Oct
Vote at MC | bar: 2013 Nov

## 2014 - Detailed Schedule
Gas Unit Commitment Coordination (OC) - 2014 Work Plan
Last updated: 7/18/14
Gas Unit Commitment Coordination (OC) | Mtg 1 | Mtg 2 | Mtg 3 | Mtg 4 | Mtg 5 | Mtg 6 | Mtg 7 | Mtg 8 | Mtg 9 | Mtg 10 | Mtg 11 | Mtg 12 | Mtg 13
| 6/23/2014 OC | 7/8/2014 OC | 7/23/2014 12-3pm | 8/5/2014 OC | 8/20/2014 1-4pm | 9/4/2014 OC | 9/16/2014 9-12pm | 10/7/2014 OC | 10/20/2014 9-12pm | 11/6/14 OC | 11/18/2014 9-12pm | 12/2/2014 OC | 12/22/2014 9-12pm
Kick Off | bar: Mtg 1
Review Problem Statement and Issue Charge | bar: Mtg 2
Develop and Review Work Plan | bar: Mtg 2
Document Interests & Priorities | bar: Mtg 2
Provide Education | bar: Mtg 2 to Mtg 13
Develop & Refine Design Components
Develop & Refine Component Options
Develop & Refine Solution Packages
Build Consensus
Polling

## Commun. Issues
Gas Unit Commitment Coordination (OC)
Detailed Communication Issues
# | ISSUE
1 | Notification Times changing hourly based on staffing and gas procurement makes timing of commitment decisions difficult
2 | Confusion around process for fuel switching (changing schedule and physical unit limitations)
3 | PJM giving estimates for run time as basis for gas purchases “firmness” of these estimates
4 | Cumbersome nature of unit commitment and fuel switch decision (example-11 phone calls for 1 unit)
5 | Process involved manual communication and logging on both ends
6 | Spotty or incomplete use of 3-part communication
7 | Not always correlating data in eMKT vs. what is communicated on the desk (via verbal communication)

## Commun. Interest Identification
Gas Unit Commitment Coordination (OC)
Interest Identification
1 | Clear communication between operators with understood obligations on both sides. Units that operator over multiple days and outside of the market- continued communications
2 | Continued communications between operators for units that operate over multiple days and are outside of the market
3 | Confirmation if communication is a directive
4 | How will fuel costs be settled if a generator is cancelled
5 | Consideration of impact on the units themselves when running with dual fuel capability that can be switched on the fly- operations and maintenance considered in the solution
6 | Dispatcher actions reflected in LMP to minimize up-lift (ERPIV)
7 | Long lead unit commitment procedures for units with greater than 24 hour startup and notification times and how it is handled in the DA Market
8 | Impact of external units that are pseudo tied and dynamically scheduled
9 | Clarity in process and impacts of switching schedules in operating day
10 | Finding appropriate way method for generation owners to communicate changing notification start times due to restrictions (currently via phone) and when outside market windows
11 | Clarification on topics being discussed in other groups
12 | Prices and dispatch instructions (to come on/off line) Prices and compensation should be consistent with dispatch instructions (to come on/off line). Binding commitment is consistent with PJM instructions
13 | Generation Owners to report costs and unit limit changes associated with operations on super cold days (i.e.- unit can operate on oil, but due to cold needs to be started with gas)
14 | While providing flexibility for fuel-limited units, do not create disparities for units that don’t have the same fuel issues.
15 | Consider limiting some of these coordination activities to times of stress or extreme events.
16 | Limiting some required coordination to times of extreme events
17 | Clarifying what it means to be available in Real Time (clarify tariff language and other items- manuals, etc.).
18 | Clear communication between operators and generators that is consistent with tariff limitations
19 | PJM operators are trained on limits of authority and are clear in instructions. No ambiguous directives. Dispatch can not issue directives beyond their ability and authority and can not over-rule the tariff
20 | Operational constraints that are being given to PJM dispatch are consistent with gas nomination timelines. Gas units - type of transportation information provided to dispatch, backup fuel (arrangements). Operational limitations so units are not over committed
21 | Cost of providing services due to rule changes needs to be kept in mind
22 | Shouldn’t limit approaches to fuel acquisition- keep flexibility. Dispatchers need to be aware of fuel and transportation availability and back up fuel arrangements (this will allow for better operational awareness)
23 | Improve generator performance
24 | Consistent with capacity market rules
25 | Sharing of operational limitation data
26 | Ensuring dispatch scheduling process results in the least cost objective is met (minimize overall costs). PJM should have a full understanding of what we are buying
27 | Fuel procurement risk is not transferred to consumers
28 | Consider tool enhancements for operators to manage processes (integrate tools)

## Commun. Matrix
Gas Unit Commitment Coordination (OC): Communication Issues
OPTIONS MATRIX
Solution Options2
# | Design Components1 | Generator Attribute Level | Priority | Status Quo | Solution Option: A | B | C | D | E
Click here for the eMKT Users Guide (Design Component Definitions)
1 | EXISTING GENERATOR DATA
1a | Emergency Min/Maximum (MW) | Unit, Schedule, Hourly Updates | 2014/2015 Winter | Entry Frequency- Upon submittal of unit-specific info to PJM Update Frequency- Daily/Hourly Entry Method- eMKT Required/Not Required- Required (if not entered, default value=0) Enforced- | Ensure all data in eMKT is accurate for next X days (up to 7 days) • Specific emphasis on forward data during hot/cold weather alerts
1b | Economic Minimum/Maximum (MW) | Unit, Schedule, Hourly Updates | 2014/2015 Winter | Entry Frequency- Upon submittal of unit-specific info to PJM Update Frequency- Daily/Hourly Entry Method- eMKT Required/Not Required- Required (if not entered, default value=0) Enforced- | Ensure all data in eMKT is accurate for next X days (up to 7 days) • Specific emphasis on forward data during hot/cold weather alerts
1c | Cost Based Start Up Costs (Hot, Inter,Cold) | Schedule (Cost Based) | 2014/2015 Winter | Entry Frequency- Daily (Cost based) Update Frequency- Daily (Cost based); Entry Method- eMKT Required/Not Required- Required (if not entered, default value=$0.00) Enforced- |  | Frequency- Ad hoc
1d | Cost Based No Load Costs | Schedule (Cost Based) | 2014/2015 Winter | Entry Frequency- Daily (Cost based) Update Frequency- Daily (Cost based) Entry Method- eMKT Required/Not Required- Required (if not entered, default value=$0.00) Enforced-
1n | Incremental Offers for Energy |  | 2014/2015 Winter
1e | Start Up Times (Hot, Inter, Cold) | Schedule |  | Entry Frequency- Daily Update Frequency- Daily Entry Method- eMKT Required/Not Required- Required Enforced- Scheduling practices / Forced Outage
1f | Notification Times (Hot, Inter, Cold) | Schedule, Hourly Updates | 2014/2015 Winter | Entry Frequency- Daily Update Frequency- Hourly (Unit Hourly Updates) Entry Method- eMKT Required/Not Required- Required (if not entered, default value=0) Enforced- | Ensure all data in eMKT is accurate for next X days (up to 7 days) • Specific emphasis on forward data during hot/cold weather alerts
1g | Cost Based Schedule | Schedule | Education | At least 1 schedule made available daily - can have more - parameter limited
1h | Price Based Schedule | Schedule | Education | Only 1 price based schedule available daily (if not parameter limited, PLS must be available in Emergency)
1i | Minimum/Maximum Run Times | Schedule | 2014/2015 Winter | Entry Frequency- Daily Update Frequency- Daily (preferred) Hourly (in practice, not preferred) Entry Method- eMKT Required/Not Required- Required (if not entered, default value= 0.0 MWh) Enforced- | Ensure all data in eMKT is accurate for next X days (up to 7 days) • Specific emphasis on forward data during hot/cold weather alerts
1j | Minimum Downtime (hourly) | Schedule |  | Entry Frequency- Daily Update Frequency- Daily Entry Method- eMKT Required/Not Required- Required (if not entered, default value= 0.0 MWh) Enforced-
1k | Temperature State Definitions Hot to Cold (hours) Hot to Intermediate (hours) | Schedule |  | Entry Frequency- Daily Update Frequency- Daily Entry Method- eMKT Required/Not Required- Required Enforced-
1l | Status | Hourly Updates | 2014/2015 Winter | The status of the generating unit is determined on a unit basis, using the Unit Detail web page. The status on the Unit Detail is used for to reflect the unit’s long-term status. This is the default for the unit. The Unit Hourly Updates web page is used to reflect real-time changes to the unit status and overwrites the unit status on the Unit Detail web page. If the status changes during real-time (for example, the unit becomes unavailable or limits change as a result of operating problems), the Operating Company uses the Unit Hourly Updates web page to provide the updated status. The following unit statuses are available from the Unit Detail web page: Economic — Indicates that a unit is available for normal economic dispatch. This is the default Emergency — Indicates that a unit is available only for Must Run — Indicates that the generating unit is self-scheduling. Unit MUST be committed. The unit is committed at Economic Min and allowed to move up to Economic Max. Not Available — Indicates that the unit is unavailable. | Ensure all data in eMKT is accurate for next X days (up to 7 days) • Specific emphasis on forward data during hot/cold weather alerts
1m | Max Weekly Energy | Schedule | 2014/2015 Winter | The maximum amount of energy, reported in MWh, that the unit can produce in one week used for study purposes. The default value is 0.0 MWh. If unit is fuel limited, it is recommended that his value be set to the default and run time restrictions be bid using the Maximum Run Time parameters. | Existing field- Can this be re-purposed for other data collection?
2 | New Generator Data
2a | Operational Restriction | Schedule | 2014/2015 Winter | NEW FIELD | Field Type: # of Operational Restrictions Definition: Default: 0
2a(I) | What is the Operational Restriction | Schedule | 2014/2015 Winter | NEW FIELD | Field Type: Dropdown and Other (Open Text) Definition: Default: None
2a(II) | Rate of Deterioration for the Operational Restriction? | Schedule | 2014/2015 Winter | NEW FIELD | Field Type: MWs and Timeframe (hr, day, week, month) Definition: Default: None
2b | Impacts of Limits
2b(I) | Run Time
2b(II) | Loading Levels
2b(III) | Price
2e | Dual Fuel Capability | Unit | 2014/2015 Winter | NEW FIELD | Field Type: Yes/No Definition: Indication whether or not unit can switch between two (or more) different fuels. Default: = No
2e(I) | Dual Fuel Availability | Schedule | 2014/2015 Winter | NEW FIELD | Field Type: Yes/No If Yes, identify which schedule to be used for fuel swap Default: = No
2e(II) | Time to Transition | Schedule | 2014/2015 Winter | NEW FIELD | Field Type: Minutes Definition: Amount of time in minutes to transition from one fuel type to another Default: = 0
2e(III) | MW Output during Transition | Schedule | 2014/2015 Winter | NEW FIELD | Field Type: MWs Definition: MW output where unit must operate to facilitate fuel transition Default: = 0
2f | Inventory Changes (i.e. fuel tanks) |  |  | Data not currently available to PJM (potential for coordination with eFuel (IMM)
2g | Latest Deadline Time |  |  | Not currently collected
2h | Price for Latest Notification Time |  |  | Not currently collected
2i | Dynamic Minimum/Maximum Run Time
2j | Dynamic Minimum/Maximum Loading Levels
2k | Time to Start
2l | Gas Delivery Characteristics (distance to pipeline, size of pipeline, distance to city) |  |  | Handle via survey
2m | Gas Acquisition characteristics (firm/non-firm delivery contracts, quantities |  |  | Handle via survey
2n | Amount of time since last start
3 | General Parameter Data Requirements (specific data fields to be reviewed)
3a | Data is "locked down" |  |  | 12pm for next day |  | Based on Gas nomination cycle
3b | Effective date for data parameters |  |  | Can enter data for 7 days into the future
3c | Penalties or incentives to provide and update parameter data |  |  | None - Default values used if data not entered
4 | Scope, binding nature (financially & physically) of dispatcher instructions provided via phone calls for unit commitment purposes |  |  | Currently phone used for updates for unit commitments- not consistent. Commitment will honor Min Run Time in effect at time of commitment
5 | True (actual physical limits of unit) limit vs. parameter limited data (or address parameter limited schedules) | [8 empty] | Low - High
6 | Timing for scheduling during Emergency Procedures
7 | Process for dispatching limited units
8 | Fuel policy for intra-day cost offers |  | 2014/2015 Winter | NEW FIELD | Actual transactions, An Index (MMU to provide further details)
Instructions:
1Design Components - each is an "attribute" or "component" of any proposed solution. Consensus of the group should be sought on selection of a set of solution criteria.
2Solution Options - each is a solution alternative elicited from the stakeholder group that meet one of the specific solution criteria.
To complete the matrix:
1. Elicit from the stakeholder group a set of components (attributes) desired for any proposed solution. Enter a short label for each in the Design Components column.
2. If needed, enter a more detailed description of each criteria on the "Component Details" tab.
3. Using informal/non-binding voting, rate each component's priority in the final solution as "high/medium/low"
4. Elicit from the stakeholder group potential solution alternative(s) for each component. Enter a short label for each in the Solution Options columns.
5. If needed, enter a more detailed description of each potential solution option on the "Solution Details" tab.
6. Once the matrix is filled out, the group will attempt to select a single solution alternative (column) for each component (row) to form a solution "package".
Example: cells 1B, 2C, 3A, 4B, 5D could make up a solution package.
7. If consensus is achieved on a single package (Tier 1 decision-making method), this will be documented in a Consensus Proposal Report to the parent committee.
8. If not, the group will identify up to 3 possible solution packages in a comparative Proposal Alternatives Report to the parent committee (Tier 2 decision-making method).

## 2014-2015 Winter Scope Matrix
Gas Unit Commitment Coordination (OC): Communication Issues
OPTIONS MATRIX
Solution Options2
# | Design Components1 | Priority | Status Quo | Solution Option: A | B | C | D | E
Click here for the eMKT Users Guide (Design Component Definitions)
1 | EXISTING GENERATOR DATA
1 | Existing Data Accuracy- Emergency Min/Max | 2014/2015 Winter | Frequency: Daily/Hourly Updates Updates: Some updates are provide verbally | Ensure data accuracy in eMKT for next X days (up to 7 days) Frequency: Same Updates: Entered in eMKT During What Time Periods: Specific emphasis during Cold/Hot Weather Alert, Max Emergency, Generation Alert, Weather/Environment Emergency, Sabotage/Terrorism Emergencies Reference: Manual 13
2 | Existing Data Accuracy- Economic Min/Max | 2014/2015 Winter | Frequency: Daily/Hourly Updates Updates: Some updates are provide verbally During What Time Periods: | Ensure data accuracy in eMKT for next X days (up to 7 days) Frequency: Same Updates: Entered in eMKT During What Time Periods: Specific emphasis during Cold/Hot Weather Alert, Max Emergency, Generation Alert, Weather/Environment Emergency, Sabotage/Terrorism Emergencies Reference: Manual 13
3 | Existing Data Accuracy- Notification Times | 2014/2015 Winter | Frequency: Daily/Hourly Updates Updates: Some updates are provide verbally During What Time Periods: | PJM, MMU, GO shall determine the notification time, and appropriate bandwidth around those notification times, for each generator as part of the previously approved MIC problem statement in 2012(Joel / Joe C. to provide appropriate description of this requirement) See '2a. Component Details' tab for more background information. GOs to ensure data accuracy in eMKT for next X days (up to 7 days) Frequency: Same as status quo Updates: Entered in eMKT During What Time Periods: Specific emphasis during Cold/Hot Weather Alert, Max Emergency, Generation Alert, Weather/Environment Emergency, Sabotage/Terrorism Emergencies Data check: If the notification time that is entered is outside of the bandwidth agreed to by aforementioned process, GOs will need to enter in a reason and duration for the change. Reference: Manual 13, Manual 10, Manual 14D
4 | Notification Time field Change Alert | 2014/2015 Winter | No current notification to dispatch if any of the unit parameters change. | Internal PJM Change: If the notification time changes, Dispatch needs to be alerted of the change- In progress for tool changes/requirements
5 | Existing Data Accuracy- Minimum Run Times | 2014/2015 Winter | Frequency: Daily Updates: Some updates are provide verbally During What Time Periods: | Ensure data accuracy in eMKT for next X days (up to 7 days) Frequency: Same Updates: Entered in eMKT During What Time Periods: Specific emphasis during Cold/Hot Weather Alert, Max Emergency, Generation Alert, Weather/Environment Emergency, Sabotage/Terrorism Emergencies Reference: Manual 13
1e | Existing Data Accuracy- Unit Status
6 | Existing Data Accuracy- Unit Status | 2014/2015 Winter | Frequency: Daily/Hourly Updates Updates: Some updates are provide verbally During What Time Periods: | Ensure data accuracy in eMKT for next X days (up to 7 days) Frequency: Same Updates: Entered in eMKT During What Time Periods: Specific emphasis during Cold/Hot Weather Alert, Max Emergency, Generation Alert, Weather/Environment Emergency, Sabotage/Terrorism Emergencies Reference: Manual 13
7 | Last Updated Field | 2014/2015 Winter | Data currently not collected | eMkt needs to provide the time the unit parameters were last updated so that Generation Owners know when the information was last updated, so they can ensure compliance with PJM's request to ensure data is accurate.
8 | New Data- Operational Restrictions (3 fields) # of Operation Restrictions- Schedule What is Operation Restriction- Schedule Remaining MW/Duration- Schedule | 2014/2015 Winter | Data currently not collected | Initial Data Population: October Generator survey On-going data update: eMKT - longer term solution Reference: Data Dictionary
| New Data- Dual Fuel (4 fields) Dual Fuel Capability- Unit Dual Fuel Availability- Schedule Time to Transition- Schedule MW Output during Fuel Transition- Schedule | 2014/2015 Winter
| New Data- Fuel Policy for inter-day cost offers | 2014/2015 Winter
9 | New Data- Dual Fuel (4 fields) Dual Fuel Capability- Unit Dual Fuel Availability- Schedule Time to Transition- Schedule MW Output during Fuel Transition- Schedule | 2014/2015 Winter | Data currently not collected | Initial Data Population: Generator owner to add in eMKT On-going data update: At Unit and Schedule level Reference: Data Dictionary
| New Data- Fuel Policy for inter-day cost offers | 2014/2015 Winter
| Reinforce Procedure for unavailable units called in RT | 2014/2015 Winter
10 | New Data- Fuel Policy for inter-day cost offers | 2014/2015 Winter | Submittal Process: Fuel policy submitted in MA tool- CODA (Cost Offer Data Application) | Submittal Process: Fuel policy submitted in MA tool- MIRA (Member Information Reporting Application)- 11/2014
11 | File upload capability for existing and new data fields | 2014/2015 Winter (?) | ?? | eMkt users will be able to submit the updates to existing data fields as well as the new data required to PJM via an XML upload as well as via the eMKT user interface.
12 | Reinforce Procedure for unavailable units called in RT | 2014/2015 Winter |  | Reference: Manual 13 (In Progress with C. Pilong)
13 | Long Lead Units with >32 hr. time to start | 2014/2015 Winter |  | Long lead time units (prior to DA) called on by PJM, in anticipation of a Cold/Hot Weather Alert, Max Emergency, Generation Alert, Weather/Environment Emergency, Sabotage/Terrorism Emergencies will be: -Committed into the DA Market with the cost and unit parameters communicated to PJM at the time of the committment -Cost-capped at the cost offer provided to PJM -Trigger the increase to the DASR (Day Ahead Synchronous Reserve) Margin, .......words from ERPIV -Will run for either the maximum of their min run time or the profile provided by PJM at the time of the committment Reference: Manual 13 (In Progress with C. Pilong) PJM will use an internal long-lead tool to identify these units.
14 | Operator communication clarification | 2014/2015 Winter |  | Reference: Manual 13 (In Progress with C. Pilong)
15 | Cost Based Schedule Updates | 2014/2015 Winter | Frequency: Daily Updates Current rule allows only allows units which are asked to run beyond DA schedule to switch schedules | Frequency: On an hourly basis, cost based schedules may be made available / unavailable based on the costs available to the generator During What Time Periods: 4 hours and beyond the current hour (i.e. there will be a three-hour block of time, the current hour and the next 2 hours where generators will not be able to change their cost-based hours) The reason for the 3-hour lock is to allow the two-hour look-ahead economic dispatch engine to dispatch units based on the data submitted at the time the dispatch engine is running and optimizing the resources. How is this done: By changing the availability of unit schedules previously ubmitted in the DA market. Situations When This is Allowed: -Resources with NO Day Ahead Commitments AND not picked up in the Reliability Assessment & Commitment Run -Resources Extended Beyond DA Scheduled Commitment Reference: Manual 11
16 | Market Timing | Long Term | DA Market closes at 1200. Rebidding period 1600-1800. RAC run 1800 | Shorten rebid period to 1600-1700. Run RAC at 1700. Inform Gos of RAC commitmenets by 1730 to allow time to purchase gas by 1800. Coordinate changes with DA/Gas market timing changes. Longer Term issue as tariff changes would be required

## Issue Topics
Gas Unit Commitment Coordination (OC)
Issue Topics
# | TOPIC | Priority | Education Materials/ Topics
1 | “Firmness” Binding PJM operator unit commitment decisions outside of Day-Ahead market (focus on communications). | Before 2014 / 2015 Winter | 1- Transcription tapes 2- Approach to scheduling for the day 3- Section 4.2.4 of PJM Manual 01 distinguishes dispatch or operating instructions from directives overview 4- How physically and financially binding are these dispatch communications?
2a | Obligations of PJM capacity units with respect to fuel availability | Need to define what is means today Further clarification will be part of High Availability Capcacity Stakeholder Process Can we even get away from it mattering, in Ops, if a unit is capacity or not? | 1-Education from CSTF and/or RPM 2- Discuss definition of obligation (to bid into DA Market and to make unit available)
2b | How the following are defined and considered: o Economic vs. reliability outages o Outages that impact Equivalent Forced Outage Rate Peak (EFORp) o Outages considered out of management control | Before 2014 / 2015 Winter For what it means today for our existing definitions | 1- Penalties and incentives for providing PJM the data it requires (e.g. startup & notification times, dual fuel capability, costs, etc)
3a | PJM unit commitment practices for units requiring significant advance notice for fuel procurement. | Discuss and review topics together
3b | Long lead unit commitment procedures for units with greater than 24 hour startup and notification times.
3c | Methods to ensure long lead generation commitments are accurately reflected in Day- Ahead market. | Before 2014 / 2015 Winter For what it means today for our existing definitions | 1- Discuss how manually committed units are handled in the DA 2- Close coordination with Unit Market Offer problem statement
3d | Flexibility of generator startup time and notification time data fields in unit offer data. Can the existing data fields accurately model the situations seen in January? Do the existing market rules support this? | Before 2014 / 2015 Winter For what it means today for our existing definitions | 1- Review current data that is provided by generators and discuss additional data that can be provided 2- Review what the flexibility is with generator start up notification time today and is what is in place sufficient?
4a | Ability to track dual fuel capability and availability in real-time, including requirements and rules for a generator to switch schedules | Before 2014 / 2015 Winter For what it means today for our existing definitions
4b | Requirements and tools for managing limited fuel availability (to include units whose primary fuel may not be natural gas but that require gas to start) and unit flexibility parameters (e.g. units that may be able to get some gas to run during peak hours only) PJM “Cancellation Costs” recovery for generators cancelled prior to expected run times in real time | Before 2014 / 2015 Winter For what it means today for our existing definitions | 1- Review all fuel types and requirements 2- Review different types of scenarios for cancellation costs when a generator is following PJM Dispatch instruction.

## 2a. Component Details
Gas Unit Commitment Coordination (OC)
COMPONENT DETAILS
Instructions: Complete this form as needed. Design components should be populated from the Options Matrix.
Design Component |  | Detailed Description
1 | Notification Times | Link the previously approved startup and notification time rules. Presentation: http://www.pjm.com/~/media/committees-groups/committees/mic/20120314/20120314-item-03-unit-notification-and-startup-times-proposal.ashx Manual changes: Material Manual 10 – http://www.pjm.com/~/media/committees-groups/committees/mic/20120509/20120509-item-12b-manual-10-revisions.ashx Material Manual 13– http://www.pjm.com/~/media/committees-groups/committees/mic/20120509/20120509-item-12a-manual-13-revisions.ashx Material Manual 14D– http://www.pjm.com/~/media/committees-groups/committees/mic/20120509/20120509-item-12c-manual-14d-revisions.ashx
2 |  | <enter detailed description of this component>
3 |  | <enter detailed description of this component>
4 |  | <enter detailed description of this component>
5 |  | <enter detailed description of this component>

## 2b. Solution Details
Gas Unit Commitment Coordination (OC)
SOLUTION DETAILS
Instructions: Complete this form as needed. Potential solutions should be populated from the Proposal Matrix
Package Solutions2
| A | B | C | D | E
1
2
3
4
5

## 3. Package Matrix
Gas Unit Commitment Coordination (OC)
PACKAGE/ PROPOSAL MATRIX
Instructions:
1. Copy over design component, priority, and status quo columns from options matrix
2. Complete individual packages in columns by selecting individual component options from the options matrix.
Packages
# | Design Components | Priority | Status Quo | A | B | C | D | E
1
2
3
4
5
6
7
8
9 | [8 empty] | Low
10 | [8 empty] | Low - Medium
Low - High
Medium
Medium - High
High

## Parking Lot
Gas Unit Commitment Coordination (OC)
Parking Lot
Instructions: Use this space to document any items not specific to another topic area.
Description

## Education Materials
Gas Unit Commitment Coordination (OC)
Education Materials
Item | Location/Link
Communication Issue Transcript | http://www.pjm.com/~/media/committees-groups/committees/oc/20140708/20140708-item-20e-communication-transcript.ashx
Operations Approach to a Peak Day | http://www.pjm.com/~/media/committees-groups/committees/oc/20140708/20140708-item-20e-operations-approach-to-a-peak-day.ashx
Gas Scheduling Issues Operator Communications | http://www.pjm.com/~/media/committees-groups/committees/oc/20140723-gas/20140723-gas-scheduling-communication-issues-presentation.ashx
Gas Unit Commitment Communication Initial Proposal for Existing and New Data Fields | http://www.pjm.com/~/media/committees-groups/committees/oc/20140904/20140904-item-02c-gas-unit-commitment-communication-initial-proposal-for-existing-and-new-fields.ashx
Cost Based and Price Based Schedule Business Rule Presentation | http://www.pjm.com/~/media/committees-groups/committees/oc/20140904/20140905-item-02a-cost-based-and-price-based-schedule-business-rules-presentation.ashx
Manual 11 Attachment C: PJM Procedure for Cost Reimbursement | http://www.pjm.com/~/media/committees-groups/committees/oc/20140908-gas/20140908-manual-11-attachment-c-pjm-procedure-for-cost-reimbursement.ashx