## Meeting Content (hidden)
Capacity Senior Task Force Meeting Content
Meeting
| 1 | 2 | 3 | 4 | 5 | 6
| 9am-noon | 9am-noon | 9am-noon | 9am-noon | 9am-noon | 9am-noon
Topic(s) | 2012-04-12 | 2012-04-19 | 2012-04-27 | 2012-05-04 | 2012-05-22 | 2012-06-06 | 2012-06-28 | 2012-07-26 | 2012-08-01
Admin | bar: 2012-04-12
Charter | bar: 2012-04-12 to 2012-04-19
Work Plan | bar: 2012-04-12
Provide Education | bar: 2012-04-12
Document Interests | bar: 2012-04-19
Develop Design Components | bar: 2012-04-19 to 2012-04-27
Develop Solution Options | bar: 2012-04-27 to 2012-05-04
Reduce Solution Options | bar: 2012-05-04
Package Solutions | bar: 2012-05-04 to 2012-05-22
Reduce Package Options | bar: 2012-05-22 to 2012-06-06
Build Concensus | bar: 2012-06-06
Vote at MRC/MC | 2012-06-28: First Read; 2012-07-26: X
File with FERC | bar: 2012-08-01

## With dates (hidden)
2012- 2013 Capacity Senior Task Force Work Plan
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProvide Education
Proposal Development |  |  | 13 |  | 11
Decision Making | [5 empty] | 14 | 5
First Read @ MRC | [6 empty] | 20
Vote at MRC/MC
RTEP/Transmission Issues | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
Problem Investigation |  |  |  | 20
Proposal Development |  |  |  |  | 11
Decision Making | [5 empty] | 14 | 5
First Read @ MRC | [6 empty] | 20
Vote at MRC/MC
Demand Response Issues | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | Mar. 2013
üProvide Education
Document Interests |  |  |  | 20
Develop & Refine Design Components | [5 empty] | 14
Develop & Refine Solution Options | [6 empty] | 5
Develop & Refine Solution Packages
Build Consensus
First Read @ MRC
Vote at MRC/MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 |  | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01
üProvide Education
Refine Interests |  |  | 13
Refine Design Components
Develop & Refine Solution Options |  |  |  |  | 2012-10-01: 11; 2012-11-01: 14
Develop & Refine Solution Packages |  |  |  |  | 2012-12-01: 5
Build Consensus | bar: 2013-01-01 to 2013-02-01
First Read @ MRC | bar: 2013-03-01
Vote at MRC/MC | bar: 2013-04-01
FERC Filing |  |  |  |  | 2013-05-01: 2012-05-31

## 2012- printable (hidden)
2012- 2013 Capacity Senior Task Force Work Plan
Triennial Review Timing | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
üProposal Development
Build Consensus
First Read @ MRC
Vote at MRC
Vote at MC
RTEP/Transmission Issues | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01
üProvide Education
üProblem Investigation
Proposal Development
Build Consensus
First Read @ MRC
Vote at MRC
Vote at MC
Multi-Year Pricing Mechanism | 2012-07-01 | 2012-08-01 | 2012-09-01 | 2012-10-01 | 2012-11-01 | 2012-12-01 | 2013-01-01 | 2013-02-01 | 2013-03-01 | 2013-04-01 | 2013-05-01
üProvide Education
üRefine Interests
üRefine Design Components
Develop & Refine Component Options | bar: 2012-10-01 to 2012-11-01
Develop & Refine Solution Packages | bar: 2012-11-01 to 2012-12-01
Build Consensus | bar: 2013-01-01 to 2013-02-01
First Read @ MRC | bar: 2013-03-01
Vote at MRC | bar: 2013-04-01
Vote at MC | bar: 2013-05-01
FERC Filing |  |  |  | 2013-05-01: 2012-05-31

## 2013- printable (hidden)
2012- 2013 Capacity Senior Task Force Work Plan
|  |  | 2012 |  |  |  | 2013
2012 Demand Response Issues | 2012-07-01 | 2012-08-01 | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun
üProvide Education
Document Interests | bar: Oct
Develop & Refine Design Components | bar: Nov
Develop & Refine Component Options | bar: Dec to 2013 Jan
Develop & Refine Solution Packages | bar: 2013 Feb to 2013 Mar
Build Consensus | bar: 2013 Mar to 2013 Apr
First Read @ MRC | bar: 2013 Apr
Vote at MRC | bar: 2013 May
Vote at MC | bar: 2013 Jun
|  |  | 2012 | 2013 Jan: 2013
2013 Demand Response Issues | 2012-07-01 | 2012-08-01 | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov
Provide Education | bar: 2013 Jan
Document Interests | bar: 2013 Feb
Develop & Refine Design Components | bar: 2013 Feb to 2013 Mar
Develop & Refine Component Options | bar: 2013 Apr to 2013 May
Develop & Refine Solution Packages | bar: 2013 Jun
Build Consensus | bar: 2013 Jul to 2013 Aug
First Read @ MRC | bar: 2013 Sep
Vote at MRC | bar: 2013 Oct
Vote at MC | bar: 2013 Nov

## Review Items
Gas Unit Commitment Coordination (OC)
Winter 2014/2015 Scope Review Items
ID | Question/Review Item | Response
1 | Exception Process: Extension of Temporary Exception One-time Temporary Exception rules | Generation Owners are requested to contact MMU and PJM in advance to review potential concerns with reflecting unit's actual parameters. Please see Manual 11 Section 2.3.4 and Tariff Section 6.6 for details on the types of Exceptions and Modification of Temporary Exceptions process Temporary waiver to be filed for Period and Persistent Exception deadline
2 | Parameter Limited Schedule General Discussions and Review | This item was added to Gas Unit Commitment Coordination workplan to be reviewed with Post Winter 2014/2015 Scope (ID#17).
3 | Manual 11 edit clarification to clarify what can by done and by whom? | 11/11 posted version of M11 edits: When a generation resource is not scheduled in the Day-Ahead Energy Market or the Reserve Adequacy Commitment (RAC) by PJM, the Market Seller may update the cost-based schedules availability hourly three hours prior to the operating hour. The cost-based schedule made available must follow the Generation Owner’s fuel cost policy as defined in PJM Manual 15: Cost Development Guidelines. A generation resource may not change schedule availability once it has been committed by PJM for the hours in which it is committed. In order to update cost based schedule availability, the Generation Owner must select the ‘Use Cost Schedule in Real Time’ flag in eMKT (New Schedule Availability Update Tab) between 1800-2100 the day prior to the operating day. Selecting this flag will make the price-based schedule unavailable for the operating day selected.
4 | Concern with timeframe of posting M11 edits | Additional conference call scheduled for 11/12 to provide opportunity to review edits and discuss questions
5 | Intra-Day Cost Schedule Changing Process- Units committed in RT are unable to change Cost Schedules until released What about for fuel switching scenarios? | Presentation slide #19 updated with the following language: Units committed in Real Time are unable to change Cost Schedules until released. Unless fuel switching for units whose primary fuel becomes unavailable after commitment and min run time met, unit will be switched from the primary fuel to the alternate fuel by PJM if PJM dispatch determines the unit is still economic based on the alternate fuel type cost based schedule.
6 | Last Updated Date field clarity on Schedule Detail, Unit Hourly Update, and Intraday Unit Schedule Availability Update screens | Time will be displayed in EPT – eastern prevailing time
7 | Use Cost Schedule in RT flag: Schedule Availability Error- What if schedules are not available for each hour (ex- due to outages). How will system process this? | Presentation slide #23 updated with: Note 1: If flag is checked at 2100 and no schedule or more than one schedule per fuel type is made available after midnight an error message will be displayed to user. Please note: If a unit is cost switching, they must have an available schedule for each hour, however, the unit might be unavailable for a set of hours.
8 | Long lead units- if min run spans across 2 gas days, what schedule will be used? | When generation resources are committed by PJM the schedule is selected from the available schedules at the time of the commitment based on minimizing system production cost. For the second day in this example the unit may (or may not) be committed based on the schedule that was entered the day prior at 12:00 if picked up in the day ahead, 18:00 if picked up in the RAC or according to the cost switch rules if picked up in real time. Essentially the unit is no longer a long lead unit. Please see presentation slide #31 and 32 for examples.
9 | Follow up question to review mapping for Gen Db project | Initial data mapping will be available for review Q12015 and can also be viewed once fields are made available in eMKT.