## 2014 CWIP Worksheet filing
Public Service Electric and Gas Company
Annual Report of Construction Work In Progress (CWIP) in Transmission Rate Base
Federal Energy Regulatory Commission Authorized Incentive Projects
(per section 2B of PSE&G's Attachment H-10B Formula Rate Implementation Protocols)
PJM Project # | RTEP Project | Actual Projects Cost thru Dec 2014 | AFUDC Year 2009 | AFUDC Year 2010 | AFUDC Year 2011 | AFUDC Year 2012 | AFUDC Year 2013 | AFUDC 2014 | 2014 CWIP Revenue Requirement | Status | Projected In-Service Date
B0489 | Build new 500 kV transmission facilities from Pennsylvania - New Jersey border at Bushkill to Roseland (500 kV and above elements of the project) | 34481067.2823 | 78361 | [5 empty] | 31002624.1985 | Completed | May 2015
B0489.4 | Install two Roseland 500/230 kV transformers as part of the Susquehanna - Roseland 500 kV project (below 500 kV elements of the project) | 7.4506e-09 | [6 empty] | 1646580.4778 | Completed | April 2014
B1154 | North Central Reliability (West Orange Project) | 0.0099998 |  | 21495.47 | 74279.84 |  |  |  | 3895715.4197 | Completed | April 2014
B1398-B1398.7 | Mickleton - Gloucester-Camden | 160260925.2297 | [6 empty] | 16099944.2381 | Under Construction | June 2015
B1398.15-B1398.19 | Mickleton - Gloucester-Camden | 532375 | [6 empty] | 65595.9647 | Under Construction | June 2015
B1156 | Burlington - Camden Conversion | 0.21044 |  | 32642.18 | 130975.02 |  |  |  | 7020285.3297 | Completed | April 2014
B1156.13-B1156.20 | Burlington - Camden Conversion | 0.1 | [6 empty] | 461550.6612 | Completed | April 2014
B1304.1-B1304.4 | Northeast Grid Reliability Project | 211553988.1359 |  |  | 32527.35 |  |  |  | 29152116.376 | Under Construction | June - December 2015
B1304.5-B1304.21 | Northeast Grid Reliability Project | 33293621.1395 | [6 empty] | 3752144.961 | Under Construction | June - December 2015
B2436.10-B2436.91 & B2437.10- B2437.33 | Bergen Linden Corridor | 34572483.0999 | [5 empty] | 13595.93 | 1445626.1451 | Under Construction | June 2016-June 2018
|  | 474694460.2078 | 78361 | 54137.65 | 237782.21 | 0 | 0 | 13595.93 | 94542183.7717